8-Week Research Tracker

AI & Music-Based Therapy in Substance Use Disorder Recovery — Bernard G.

Tick each box as you complete a task — in Word, click the box to mark it done. Items marked ◆ are supervisor checkpoints: the three points where a stalled decision is most likely to derail the timeline. The schedule assumes a tightly-scoped scoping review or conceptual synthesis; a full systematic review with meta-analysis is not feasible in eight weeks.

# Week 1 — Scoping and framing

Milestone:  Design chosen; final research questions; one-page protocol skeleton.

Confirm the design with your supervisor (scoping review vs conceptual synthesis)

Decide: insist on the AI-plus-music intersection, or synthesise the two literatures separately

Decide substance scope (all SUD, or focus on opioid / alcohol use disorder)

Finalise the overarching research question

Finalise RQ1–RQ4 (one per pillar) and RQ5 (ethics, cross-cutting)

Read the Cochrane music therapy review (Ghetti et al., 2022)

Read an AI-in-SUD perspective (Moniz-Lewis et al., 2025)

Read an affective-computing-for-mental-health review

Draft a one-page protocol skeleton

◆ Supervisor checkpoint: sign-off on design and research questions

# Week 2 — Protocol and setup

Milestone:  Finalised protocol and tested search strings; draft introduction.

Finalise Boolean search strings for each database

Set inclusion / exclusion criteria

Choose appraisal tools (RoB 2 for RCTs, AMSTAR-2 for reviews, CASP for qualitative)

Register the protocol if eligible (PROSPERO)

Set up a reference manager (Zotero / EndNote)

Create the screening log

Build the extraction template, keyed to the four pillars

Draft the Introduction / background section

# Week 3 — Search and screening

Milestone:  PRISMA flow numbers; screened set; draft methods.

Run searches across all databases

Export results and deduplicate

Screen titles and abstracts against the criteria

Record all screening decisions in the log

Begin full-text screening

Draft the Methods section (search strategy and criteria)

# Week 4 — Full-text screening and appraisal

Milestone:  Final included-study set; roughly half of extraction done.

Complete full-text screening

Finalise the set of included studies

Begin quality appraisal

Begin data extraction into the pillar matrix

◆ Supervisor checkpoint: review of the included-study set before extraction goes too far

# Week 5 — Appraisal, extraction, and early synthesis

Milestone:  Completed evidence table.

Finish quality appraisal

Complete data extraction

Tag each finding: established / emerging / speculative

Synthesise the emotional-regulation pillar

Synthesise the craving pillar, including the craving-cue paradox

Finalise the evidence table

# Week 6 — Synthesis and draft findings

Milestone:  Full synthesis notes; draft findings (and framework if pursuing Option B).

Synthesise the self-expression pillar

Synthesise the personalised-support pillar

Identify cross-pillar themes

Identify ethics themes

Draft the Results / Findings section

If pursuing Option B: draft the proposed framework

# Week 7 — Full draft

Milestone:  Complete first full draft to supervisor.

Draft the Discussion (mapped to pillars, mechanisms, strength of evidence)

Draft the Limitations section

Draft the Ethics section

Draft the Conclusion

Assemble the complete draft end to end

◆ Supervisor checkpoint: send the full draft to your supervisor

# Week 8 — Revision and verification

Milestone:  Verified final draft.

Incorporate supervisor feedback

Verify every empirical claim against its primary source

Check terminology precision (music therapy / MBI / consumer listening; SUD severity)

Check person-first language throughout

Finalise references and citation formatting

Finalise the PRISMA flow diagram

Final proofread

Export the verified final draft